## Sheet1
CLIENT ACTION TAKEN SHEET OF Morth Dashboard
S.N. | SEVERITY | VULNERABILITIES NAME | URL | STATUS | AUDITOR STATUS | DESCRIPTION
1 | High | Password Replay (Hash attack) is possible | https://morth-staging.prodios.com/ | closed | closed | We have implmented password payload expiration check (15 seconds).
2 | High | It is possible to upload malicious (.exe) file in the application. | https://morth-staging.prodios.com/ | open | closed | The file uploads feature is not being worked on and is disabled in production. We have removed the API and page to view and upload files.
3 | High | Sensitive Information (credit card number) disclose in this application. | https://morth-staging.prodios.com/ | closed | discarded | Array of Coordinates (Latitude and Longitude) are misidentified as Credit Card Numbers in accompanied Report.
4 | Medium | Clickjacking attack is possible in application. | https://morth-staging.prodios.com/ | closed | closed | Added "X-Frame-Options "DENY";" header.
5 | Medium | Banner grabbing (application is displaying Server version and web technology version which may help attacker to learn more about his target) is possible in the application. | https://morth-staging.prodios.com/ | still open | closed | We have removed the version details from the "Server" header as per report. Complete removal of "Server" header is not possible due to us not using custom build of nginx.
6 | Medium | Old and vulnerable version of library used in this application. | https://morth-staging.prodios.com/ | still open | discarded | This is a not a direct dependency of our application and hence can't be upgraded by us.
7 | Medium | Security headers such as missing in Application. | https://morth-staging.prodios.com/ | closed | closed | Added requsted security headers.
8 | Medium | Runtime error message displayed to the end user in the application. | https://morth-staging.prodios.com/ | still open | closed | Added custom error pages to handle 400, 401, 402, 403, 404, 500, 501, 502, 503 error codes.
9 | Medium | Forceful Browsing is possible in the application. | https://morth-staging.prodios.com/ | still open | discarded | The specific file referenced in the report is a static, publicly accessible guide on how to use the application. It is not intended to be confidential. Kindly inform us if there are any other files or pages that may be vulnerable to forceful browsing.
10 | Medium | CORS (Cross Origin Resource Sharing) Misconfiguration is possible in Application. | https://morth-staging.prodios.com/ | closed | closed | We have added allowed domains to "Access-Control-Allow-Origin" header.
11 | Medium | Multiple ports open in this application. | https://morth-staging.prodios.com/ | closed | discarded | Since this is a shared staging server, we are hosting multiple applications. On production only port 80 and 443 are open.
| Medium | stack trace error | https://morth-staging.prodios.com/#/vahan | open | screenshot attached
| LOW | path set to route | https://morth-staging.prodios.com/ | open
12 | LOW | There is no change password used in the application. | https://morth-staging.prodios.com/ | open | closed | Added option to change password in profile dropdown menu.
14 | LOW | Some configuration files disclose in this application. | https://morth-staging.prodios.com/ | open | discarded | "robots.txt" file is being used to control which pages are visible to search engines. This needs to be public and poses no specific risks.
14 | LOW | There is no session timeout in application. | https://morth-staging.prodios.com/ | still open | discarded | This is as per client requirements, as dashboard in being displayed for long periods without any user interaction.
15 | LOW | The application does not maintain audit trail properly where all user activities have to be logged. In-case a malicious user tries to attack the application; the application will not be able to trace the attacker. | https://morth-staging.prodios.com/ | open | discarded | This would take a lot of development effort. Since most of the applicaton is view only and almost no mutations are being done, for us maintaining request logs is enough which is being done at web-server level.
16 | LOW | Max length is not set properly in this application | https://morth-staging.prodios.com/#/login | open
17 | LOW | change password module is not working properly | https://morth-staging.prodios.com/#/ | open